## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000130/2020-2021 | 1066/MAAD | 14/10/2020 | 13/11/2020 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.23 | 22.17 | 87.86 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 11/02/2022 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN CHANDIPUR Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000140/2020-2021 | 1121/MAAD | 09/11/2020 | 09/12/2020 | BHOLANATH CONSTRUCTION | 57.22 | 54.97 | 96.07 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | SM/06848 | Retrofitting | Laying of UPVC pipeline &Construction of Pavement & others Allied Work at Charianantapur W/S Scheme under Malda Arsenic Area W/S Divn.PHE. Dte. |  |  | ORD/000208/2021-2022 | 1060/MAAD | 03/08/2021 | 17/09/2021 | BANIK BROTHERS | 4.78 | 0.03 | 0.6 | 0
Total | [13 empty] | 96.62 | 77.17 | 79.87