## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme | SM/06849 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000139/2020-2021 | 1120/MAAD | 09/11/2020 | 24/12/2020 | MILLENNIUM ENTERPRISE | 70.6 | 33.71 | 47.75 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme | SM/06849 | Retrofitting | Transfer of funds from the account of Implementing Agencies to Singles Nodal Account (Escrow Account) under Jal Jeevan Mission. |  |  | VCH/001219/2021-2022 | 580 | 29/03/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 23.94 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme | SM/06849 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nagharia Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000251/2020-2021 | 88/MAAD | 15/01/2021 | 14/02/2021 | M/S PARIMAL DAS | 0.52 | 0.52 | 100 | 0
Total | [13 empty] | 95.06 | 34.23 | 36.01