## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | SM/06986 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000142/2020-2021 | 1129/MAAD | 11/11/2020 | 11/12/2020 | BEE GEE CONSTRUCTION | 34.65 | 66.36 | 191.52 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | SM/06986 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sahajalalpur Water Supply Scheme (Habitation- Sarkar Para, Chowdhury Para) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000264/2022-2023 | 1866/MAAD | 28/09/2022 | 12/11/2022 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.98 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | SM/06986 | Retrofitting | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. |  |  | BILL/00346/2023-2024 |  | 22/09/2023 | 22/09/2023 | DIGITEK SOLUTIONS | 0.42 | 0 | 0 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | SM/06986 | Retrofitting | SUPPLY OF THE FOLLOWING COMPUTER ACCESSORIES WITH SERVICE CHARGE FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  |  | BILL/00239/2023-2024 |  | 24/08/2023 | 24/08/2023 | DIGITEK SOLUTIONS | 0.42 | 0 | 0 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | SM/06986 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  |  | BILL/00219/2023-2024 | C082336196084 | 24/08/2023 | 24/08/2023 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.1 | 0 | 0 | 0
Total | [13 empty] | 40.58 | 66.36 | 163.53