## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000307/2021-2022 | 1649/MAAD | 03/11/2021 | 18/12/2021 | GOUTAM SAHA | 14.69 | 14.25 | 97.04 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (East Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000563/2021-2022 | 1652/MAAD | 03/11/2021 | 18/12/2021 | S. R. CONSTRUCTION | 10 | 17.95 | 179.48 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Laying of HDPE pipe 20mm dia at Lalapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000094/2022-2023 | 969/MAAD | 11/05/2022 | 26/05/2022 | GOUTAM SAHA | 3.39 | 3.39 | 100 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Laying of HDPE pipe 20mm dia alongwith providing FHTCat Mahabbatpur East Zone water supply Scheme of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000095/2022-2023 | 968/MAAD | 11/05/2022 | 26/05/2022 | S. R. CONSTRUCTION | 3.73 | 3.73 | 100 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme (Mouza- Itakhola, Habitation- Tekra) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000032/2022-2023 | 736/MAAD | 19/04/2022 | 19/05/2022 | DHRITIPALI | 2.34 | 2.26 | 96.6 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Talimnagar Zone-II Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000355/2021-2022 | 1724/MAAD | 18/11/2021 | 18/12/2021 | S & G CONSTRUCTION | 3.82 | 3.32 | 87.06 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000309/2021-2022 | 1651/MAAD | 03/11/2021 | 18/12/2021 | DHRITIPALI | 7.16 | 0 | 0 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (West Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000311/2021-2022 | 1653/MAAD | 03/11/2021 | 02/01/2022 | USHA ENTERPRISE | 39.32 | 19.2 | 48.83 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak Water Supply Scheme (Village- Parbatya) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000254/2022-2023 | 1832/MAAD | 27/09/2022 | 11/11/2022 | DHRITIPALI | 4.22 | 4.19 | 99.14 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak water Supply Scheme in Gopinathpur villages within English Bazar Block in Malda District under Malda Arsenic Area Water Supply Division PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000308/2021-2022 | 1650/MAAD | 03/11/2021 | 18/12/2021 | UTTAM KUMAR GHOSH | 19.1 | 16.86 | 88.24 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000498/2021-2022 | 1651/MAAD | 03/11/2021 | 18/12/2021 | DHRITIPALI | 10 | 6.84 | 68.39 | 1
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 194/MAAD | 11/02/2022 | 11/02/2022 | Resource Division | 14.54 | 0 | 0 | 0
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Service connection Charges/ Security Deposit for Itakhola AIRP of Itakhola distribution zone under Malda Arsenic Area W/S Division. |  |  | BILL/00238/2024-2025 | C092441964963 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0 | 0
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | SM/08760 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, and 3 (three) months Trial Run & 9 (nine) months Operation & Maintenance of 8 .0 CuM/Hr capacity Arsenic & Iron Elimination Plants of Gobordanga model (Pressure type) including 1 (one) Compressor Room of internal size [3.6mtr(L) x 3.00 mtr(B) x 3.15mtr(H)] and sludge disposal arrangement for Mahabbatpur (East Zone) Water Supply Scheme under Malda Arsenic Area W/S. Division, PHE Dte in the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000324/2021-2022 | 1764/MAAD | 25/11/2021 | 02/08/2025 | MERCURY ENGINEERING COMPANY | 30 | 18 | 60 | 50
Total | [13 empty] | 166.1 | 109.98 | 66.21