## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Enayetpur Water Supply Scheme( Enayetpur mouza) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000354/2021-2022 | 1757/MAAD | 24/11/2021 | 08/01/2022 | A. B. CONSTRUCTION | 24.33 | 0 | 0 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Laying of HDPE pipe 20mm dia at Enayetpur Mouza for installation of FHTC under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000530/2021-2022 | 361/MAAD | 07/03/2022 | 06/04/2022 | A. B. CONSTRUCTION | 3.03 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area (Mouza Enayetpur part, Miragram) & others Allied works at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000051/2022-2023 | 825/MAAD | 28/04/2022 | 27/06/2022 | GOBINDA ENTERPRISE | 36.64 | 0 | 0 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakipur (Laddutola) under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000223/2022-2023 | 1473/MAAD | 29/07/2022 | 12/09/2022 | ABHIJIT ENTERPRISE | 4.84 | 0 | 0 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Repairing of pipe line by laying of UPVC pipeline at Miragram Mouza for installation of FHTC at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000157/2022-2023 | 1170/MAAD | 13/06/2022 | 28/07/2022 | GOBINDA ENTERPRISE | 4.82 | 0 | 0 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Laying of 63 mm dia UPVC Pipe and 20 mm dia HDPE pipe and other allied works at Miragram for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000268/2022-2023 | 1870/MAAD | 28/09/2022 | 12/11/2022 | GOBINDA ENTERPRISE | 3.93 | 0 | 0 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Laying UPVC pipe and installation of Street Stand post at Sekhpura purbapara under Enayetpur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000046/2023-2024 | 945/MAAD | 23/05/2023 | 07/07/2023 | ABHIJIT ENTERPRISE | 3.53 | 0 | 0 | 0
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Salabadganj Paschim Para under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000200/2022-2023 | 1477/MAAD | 29/07/2022 | 12/09/2022 | M/S. AYUSH BUILDERS | 4.77 | 0 | 0 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Laying of 90 mm dia UPVC Pipeline and other allied works at Salabadganj for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000272/2022-2023 | 1873/MAAD | 28/09/2022 | 12/11/2022 | M/S. AYUSH BUILDERS | 2.66 | 0 | 0 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | SM/09591 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24011.79 | 0 | 0