## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-II |  | ORD/000566/2021-2022 | 2042/MAAD | 29/12/2021 | 29/12/2022 | M/S PARIMAL DAS | 3.85 | 2.46 | 63.86 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bholaichak Water Supply Scheme (Bholaichak, Pakakot, Chakdomai, Sahabajpur Sailapur, Golapganj, Larchak, Chaklalu, Fatepur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000378/2021-2022 | 1994/MAAD | 27/12/2021 | 27/03/2022 | BANIK BROTHERS | 128.52 | 128.21 | 99.76 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Balutola,Akandabaria,Charkatola,Pakakot,Umakanta,Nowda,Ramnagar,Domaichak ,Naldahari&Choyantola under command area of Bholaichak Water Supply Scheme Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000052/2022-2023 | 826/MAAD | 28/04/2022 | 27/06/2022 | BANIK BROTHERS | 75.53 | 74.82 | 99.05 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of UPVC pipe line 110mm,90mm&75mm dia at Bholaichak Raghunathtola, Domaichak Nayatola, Natun Shiv mandir para, Sahabajpur Budhamore, Sahabajpur Ghosh para,horismandal para balufaranad Sardaha & others Allied works at Bholaichak W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000053/2022-2023 | 827/MAAD | 28/04/2022 | 12/06/2022 | GOBINDA ENTERPRISE | 21.46 | 21.44 | 99.91 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Bahirbona,Milik sultanpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000060/2022-2023 | 912/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.67 | 4.66 | 99.78 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Fetepur Chaipara,Nowda under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000062/2022-2023 | 914/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.81 | 4.8 | 99.93 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Ragunath Tola,Attaramtola& Ramdhantola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000257/2022-2023 | 1835MAAD | 27/09/2022 | 27/10/2022 | BANIK BROTHERS | 4.04 | 4.02 | 99.66 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Balufara,Banstola & Charkatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000256/2022-2023 | 1834MAAD | 27/09/2022 | 27/10/2022 | BANIK BROTHERS | 4 | 3.99 | 99.77 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Akandabaria, Chakdomai & Umakantatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000059/2022-2023 | 911/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.71 | 4.69 | 99.67 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Suknagar,Fatepur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000061/2022-2023 | 913/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.74 | 4.72 | 99.61 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at balutola,Kazichak & Srinibashpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000255/2022-2023 | 1833/MAAD | 27/09/2022 | 27/10/2022 | BANIK BROTHERS | 4.4 | 4.38 | 99.64 | 1
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 195/MAAD | 11/02/2022 | 11/02/2022 | Resource Division | 38.57 | 0 | 0 | 0
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1340/MAAD | 18/07/2022 | 18/07/2022 | Resource Division | 7.01 | 0 | 0 | 0
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09646 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
Total | [13 empty] | 24229.54 | 258.2 | 1.07