## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-I |  | ORD/000567/2021-2022 | 2041/MAAD | 29/12/2021 | 29/12/2022 | SUBRATA SAHA | 4.5 | 2.1 | 46.65 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-II | Junior Engineer-II | ORD/000331/2021-2022 | 1743/MAAD | 24/11/2021 | 23/01/2022 | BEE GEE CONSTRUCTION | 56.38 | 24.8 | 43.99 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-II | Junior Engineer-II | ORD/000565/2021-2022 | 1743/MAAD | 24/11/2021 | 24/12/2021 | BEE GEE CONSTRUCTION | 70 | 24.35 | 34.79 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Mokshedpur, Sayedpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000042/2022-2023 | 818/MAAD | 28/04/2022 | 27/06/2022 | BEE GEE CONSTRUCTION | 76.47 | 73.06 | 95.55 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Natibpur, Purba Chandpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000043/2022-2023 | 819/MAAD | 28/04/2022 | 12/06/2022 | M/S PRATIMA CONSTRUCTION | 27.81 | 23.04 | 82.84 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Selimpur, Uttar Roypur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000114/2022-2023 | 1016/MAAD | 12/05/2022 | 11/07/2022 | NEOGI ENTERPRISE | 53.8 | 36.92 | 68.62 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Laying of 90 mm dia UPVC Pipe line at Tatipara for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000201/2022-2023 | 1449/MAAD | 29/07/2022 | 12/09/2022 | SURAJIT MANDAL | 4.37 | 4.36 | 99.72 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Laying of 75 mm dia uPVC Pipe line at Jhabri Tola, Tati Para, Colony & Chatra Para for installation of FHTC under Bamongram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000162/2022-2023 | 1175/MAAD | 13/06/2022 | 28/07/2022 | BEE GEE CONSTRUCTION | 4.82 | 4.82 | 99.94 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Jalalpur, Purba Chandpur, Selimpur, Uttar Raypur for installation of FHTC under Bamangram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000302/2022-2023 | 2034/MAAD | 16/11/2022 | 31/12/2022 | BEE GEE CONSTRUCTION | 7.28 | 7.27 | 99.9 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Laying of 90 mm dia UPVC Pipe line at Jhabritola, Khariyadoba for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000202/2022-2023 | 1450/MAAD | 29/07/2022 | 12/09/2022 | SURAJIT MANDAL | 1.64 | 1.64 | 99.93 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1703/MAAD | 21/09/2022 | 21/09/2022 | Resource Division | 3.08 | 0 | 0 | 0
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | SM/09647 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
Total | [13 empty] | 24233.38 | 202.35 | 0.84