## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation Nurnagar, Bakhtarband, Sabdulpur, Sukdebpur, Harinagar, Niyoginagar, Mohanpur Khas, Mohanpur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000328/2021-2022 | 1739/MAAD | 24/11/2021 | 23/01/2022 | M/S AMIT KUMAR GUPTA | 59.9 | 59.86 | 99.94 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC pipe 200mm,160mm,125mm&110mm dia at Sukpara& others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000510/2021-2022 | 395/MAAD | 08/03/2022 | 22/04/2022 | DEY CONSTRUCTION | 30.43 | 30.41 | 99.93 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC pipe 90mm dia at Mahonpur & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000515/2021-2022 | 346/MAAD | 07/03/2022 | 21/04/2022 | ABHIJIT CONSTRUCTION | 3.78 | 3.74 | 98.77 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC pipe 90mm dia at Manoj Master para & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000516/2021-2022 | 347/MAAD | 07/03/2022 | 21/04/2022 | MAHA MAYA CONSTRUCTION | 3.61 | 3.59 | 99.6 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation-Sukpara,Kumvira&Hatatpara) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000047/2022-2023 | 821/MAAD | 28/04/2022 | 27/06/2022 | FUTURE | 76.04 | 75.72 | 99.59 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Nurnagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000138/2022-2023 | 1151/MAAD | 13/06/2022 | 28/06/2022 | M/S AMIT KUMAR GUPTA | 3.9 | 3.89 | 99.72 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Bakrabad & Sabdalpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000139/2022-2023 | 1152/MAAD | 13/06/2022 | 28/06/2022 | M/S AMIT KUMAR GUPTA | 4.16 | 4.15 | 99.66 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Sukdebpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000140/2022-2023 | 1153/MAAD | 13/06/2022 | 28/06/2022 | M/S AMIT KUMAR GUPTA | 4.04 | 4.04 | 99.79 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Mohanpur khas & Mohanpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000141/2022-2023 | 1155MAAD | 13/06/2022 | 28/06/2022 | M/S AMIT KUMAR GUPTA | 3.9 | 3.88 | 99.66 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Hadinagar & Neoginagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000142/2022-2023 | 1154/MAAD | 13/06/2022 | 28/06/2022 | M/S AMIT KUMAR GUPTA | 3.93 | 3.91 | 99.55 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC Pipe Line of 90mm at Sabdalpur Jamaipara & Kubhira for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000215/2022-2023 | 1463/MAAD | 29/07/2022 | 12/09/2022 | FUTURE | 3.06 | 3.05 | 99.76 | 1
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC Pipe Line of 75 mm dia at Godhantola,Mahis Mandal para,Bakrabad char & Sukpara for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000216/2022-2023 | 1464/MAAD | 29/07/2022 | 12/09/2022 | FUTURE | 4.71 | 4.71 | 99.93 | 1
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Sabdalpur, Sukpara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000259/2022-2023 | 1837/MAAD | 27/09/2022 | 27/10/2022 | FUTURE | 4.4 | 4.39 | 99.89 | 1
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Mohanpur,Godhantola under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000260/2022-2023 | 1838/MAAD | 27/09/2022 | 27/10/2022 | FUTURE | 4.13 | 4.12 | 99.81 | 1
15 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Khasmohanpur,Kumvira under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000258/2022-2023 | 1836/MAAD | 27/09/2022 | 27/10/2022 | FUTURE | 4.3 | 4.29 | 99.86 | 1
16 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Hatatpara,Ghospara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000261/2022-2023 | 1839MAAD | 27/09/2022 | 27/10/2022 | FUTURE | 4.36 | 4.34 | 99.51 | 1
17 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-II | Junior Engineer-II | ORD/000565/2021-2022 | 1743/MAAD | 24/11/2021 | 24/12/2021 | BEE GEE CONSTRUCTION | 70 | 3.19 | 4.55 | 1
18 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Laying of UPVC pipe 140mm dia at Sabdalpur Guntola & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000190/2022-2023 | 1401/MAAD | 26/07/2022 | 09/09/2022 | MAHA MAYA CONSTRUCTION | 8.18 | 7.5 | 91.75 | 1
19 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Sabdalpur Guntola under command area of Kumvira Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000294/2022-2023 | 2033/MAAD | 16/11/2022 | 31/12/2022 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 9.35 | 9.25 | 98.89 | 1
20 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. |  |  | BILL/00347/2023-2024 |  | 22/09/2023 | 22/09/2023 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0 | 0
21 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  |  | BILL/00271/2023-2024 |  | 07/09/2023 | 07/09/2023 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0 | 0
22 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  |  | BILL/00240/2023-2024 |  | 24/08/2023 | 24/08/2023 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.73 | 0 | 0 | 0
23 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | SM/09648 | Retrofitting | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2023 to 31.12.2023)= 365 days. | Assistant Engineer-I |  | ORD/000462/2022-2023 | 2389/MAAD | 30/12/2022 | 30/12/2387 | SUBRATA SAHA | 1.73 | 4.22 | 243.47 | 60
Total | [13 empty] | 312.68 | 242.26 | 77.48