## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Sisa, Bhagabanpur& others Allied works at Krishnapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000120/2022-2023 | 1021/MAAD | 12/05/2022 | 26/06/2022 | SUDIP DEY | 15.28 | 0 | 0 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09650 | Retrofitting | Providing Functional household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Krishnapur Water Supply Scheme (Jagirtola, Krishnapur Chama, Bechutola, Rajutola, Guntola, Mandai, Mandaichaipara, Nashtola joenpur, Chakbahadurpur, Bintola, Sachitrapara, Kopatola, Krishnapur, Kacharitola & KBS) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000453/2021-2022 | 50/MAAD | 20/01/2022 | 20/04/2022 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 206.62 | 0 | 0 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09650 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24145.14 | 0 | 0