## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dariapur Water Supply Scheme(Mouza-Laxmipur,Baisnabnagar) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000315/2021-2022 | 1728/MAAD | 24/11/2021 | 23/01/2022 | DEY CONSTRUCTION | 46.22 | 0 | 0 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of HDPE pipe line of 20 mm dia at Birjutola,Sam Mahamand Tola,Laxmipur Villages Under Laxmipur GP under Dariapur distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000532/2021-2022 | 363/MAAD | 07/03/2022 | 06/04/2022 | DEY CONSTRUCTION | 4.81 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of UPVC pipe 90mm dia at Srikasti,Chulkani & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000519/2021-2022 | 350/MAAD | 07/03/2022 | 21/04/2022 | GIRIDHARI CONSTRUCTION | 2.9 | 0 | 0 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Munshitola,Tewari Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2022-2023 | 908/MAAD | 10/05/2022 | 25/05/2022 | DEY CONSTRUCTION | 4.81 | 0 | 0 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Baultola, Bikkol Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000057/2022-2023 | 909/MAAD | 10/05/2022 | 25/05/2022 | DEY CONSTRUCTION | 1.73 | 0 | 0 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area(Mouza Laxmipur Part, Bedrabad) & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000044/2022-2023 | 820/MAAD | 28/04/2022 | 27/06/2022 | DEY CONSTRUCTION | 53.78 | 0 | 0 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000290/2022-2023 | 2005/MAAD | 11/11/2022 | 26/12/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 0 | 0 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Dhulauri ,Hunumannagar & Bedrabad under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000013/2023-2024 | 803/MAAD | 24/04/2023 | 09/05/2023 | DEY CONSTRUCTION | 3.91 | 0 | 0 | 0
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Dariapur Mouza under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000115/2022-2023 | 1017/MAAD | 12/05/2022 | 11/07/2022 | M/S PARIMAL DAS | 56.47 | 0 | 0 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Diferent villages under Bedrabad GP (Dhulauri,Hunumannagar,Bedrabad) under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000292/2022-2023 | 2031/MAAD | 16/11/2022 | 15/01/2023 | DEY CONSTRUCTION | 56.08 | 0 | 0 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Bedrabad ,Dulauri ,Srikasti & Manasa Mandir para under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000252/2022-2023 | 1830MAAD | 27/09/2022 | 27/10/2022 | DEY CONSTRUCTION | 4.07 | 0 | 0 | 1
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of UPVC Pipe Line of 90mm &75 mm dia at Different part of Dariapur Mouza for coverage of FHTC under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000269/2022-2023 | 1871/MAAD | 28/09/2022 | 12/11/2022 | M/S PARIMAL DAS | 4.49 | 0 | 0 | 1
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of UPVC pipeline at Kochpara to faciliate of House connection & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000359/2022-2023 | 70/MAAD | 11/01/2023 | 12/03/2023 | DHRITIPALI | 6.69 | 0 | 0 | 0
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of UPVC pipe 90mm,75mm dia at Kochpara ,Bajapti & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000212/2023-2024 | 887/MAAD. | 11/05/2023 | 25/06/2023 | MADHUMITA ENTERPRISE | 9.44 | 0 | 0 | 100
15 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000289/2022-2023 | 2029/MAAD | 16/11/2022 | 31/12/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 0 | 0 | 1
16 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | SM/09652 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24218.32 | 0 | 0