## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Old 16 mile,Tingaria at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000316/2021-2022 | 1729/MAAD | 24/11/2021 | 23/01/2022 | MD. TALEB ALI | 40.17 | 0 | 0 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-New Tingaria,Beguntola,BramattatTola,KartikTola,Ghoshpara,Jallutola )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000317/2021-2022 | 1731/MAAD | 24/11/2021 | 08/01/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 33.14 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Kanchitola,V.D.O more ,Agnutola,Charbabupur,Anarditola,Dinutola,Khikirbona,Kanainagar )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000318/2021-2022 | 1730/MAAD | 24/11/2021 | 23/01/2022 | MD. TALEB ALI | 38.3 | 0 | 0 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Baisnabnagar,Habitation-Old 16 mile,16 mile band,Rameshtartola,Mahajantola,KamalTola,Guruprasad Tola,17 Mile &17 mile rail Gate )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000319/2021-2022 | 1732/MAAD | 24/11/2021 | 23/01/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 48.93 | 0 | 0 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Babupur,Habitation-Nasirtola,Radhanathtola,Mukandapur,Guljartola,Hatichapa &Babupur )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000320/2021-2022 | 1734/MAAD | 24/11/2021 | 08/01/2022 | M/S KUNDU CONSTRUCTION | 33.55 | 0 | 0 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000117/2022-2023 | 1018/MAAD | 12/05/2022 | 11/07/2022 | MANASH KUMAR SAHA | 69.64 | 0 | 0 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000146/2022-2023 | 1159MAAD | 13/06/2022 | 28/06/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.02 | 0 | 0 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola,Kamai Tola &Guruprassad Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000147/2022-2023 | 1160/MAAD | 13/06/2022 | 28/06/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.48 | 0 | 0 | 1
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Ghoshpara & Jallutola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2022-2023 | 1162/MAAD | 13/06/2022 | 28/06/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.28 | 0 | 0 | 1
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at New Agnutola &Charbabupur & Anarditola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000152/2022-2023 | 1165/MAAD | 13/06/2022 | 28/06/2022 | MD. TALEB ALI | 4.28 | 0 | 0 | 1
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000153/2022-2023 | 1166/MAAD | 13/06/2022 | 28/06/2022 | MD. TALEB ALI | 4.54 | 0 | 0 | 1
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Tingaria under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000154/2022-2023 | 1167/MAAD | 13/06/2022 | 28/06/2022 | MD. TALEB ALI | 4.41 | 0 | 0 | 1
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Kanchitola &VDO more under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2022-2023 | 1168/MAAD | 13/06/2022 | 28/06/2022 | MD. TALEB ALI | 4.4 | 0 | 0 | 1
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at 17 Mile,17Mile rail Gate,New Tingaria,Beguntola ,Bramattatola & Kartik Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000148/2022-2023 | 1161MAAD | 13/06/2022 | 28/06/2022 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.15 | 0 | 0 | 1
15 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Nasirtola, Guljartola, Vimagram, Mukundatola, under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2022-2023 | 1163/MAAD | 13/06/2022 | 28/06/2022 | M/S KUNDU CONSTRUCTION | 4.77 | 0 | 0 | 1
16 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Charbabupur under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000151/2022-2023 | 1164/MAAD | 13/06/2022 | 28/06/2022 | MD. TALEB ALI | 4.81 | 0 | 0 | 1
17 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at lalutola, sarkartola, Birnagar,Guljartola, Jaladitola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000474/2022-2023 | 608/MAAD | 31/03/2023 | 15/04/2023 | MANASH KUMAR SAHA | 5.57 | 0 | 0 | 0
18 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 11/02/2022 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
19 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Gudhuyagram Village under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000293/2022-2023 | 2032/MAAD | 16/11/2022 | 31/12/2022 | THREE BROTHERS CONSTRUCTION & CO. | 8.48 | 0 | 0 | 1
20 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 131/MAAD | 28/01/2022 | 28/01/2022 | Resource Division | 6.97 | 0 | 0 | 0
21 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 193/MAAD | 11/02/2022 | 11/02/2022 | Resource Division | 53.98 | 0 | 0 | 0
22 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 1700/MAAD | 21/09/2022 | 21/09/2022 | Resource Division | 3.7 | 0 | 0 | 0
23 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | SM/09653 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24319.17 | 0 | 0