## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | SM/09654 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sattari Mouza of Sattari Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000351/2021-2022 | 1763/MAAD | 24/11/2021 | 23/01/2022 | SUDIP DEY | 37.57 | 37.36 | 99.45 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Mobarakpur , Basantapur under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000092/2022-2023 | 966/MAAD | 11/05/2022 | 26/05/2022 | SUDIP DEY | 4.74 | 4.72 | 99.64 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Madapur , Masjidpara under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000093/2022-2023 | 967/MAAD | 11/05/2022 | 26/05/2022 | SUDIP DEY | 2.11 | 2.11 | 100 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Sattari under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000091/2022-2023 | 965/MAAD | 11/05/2022 | 26/05/2022 | SUDIP DEY | 4.82 | 4.8 | 99.69 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | SM/09654 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 23972.47 | 49 | 0.2