## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sadipur) | Assistant Engineer-II | Junior Engineer-II | ORD/000336/2021-2022 | 1740/MAAD | 24/11/2021 | 23/01/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 56.03 | 47.35 | 84.51 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Akandaberia, Paschim Janutola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000119/2022-2023 | 1020/MAAD | 12/05/2022 | 26/06/2022 | M/S MANDAL & SONS | 26.16 | 23.75 | 90.8 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Laying of UPVC Pipe line at Panchkiritola for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000301/2022-2023 | 2041/MAAD | 16/11/2022 | 31/12/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 2.64 | 2.62 | 99.5 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Mobarakpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000055/2022-2023 | 829/MAAD | 28/04/2022 | 12/06/2022 | M/S BABLU ENTERPRISE, | 11.69 | 10.08 | 86.22 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Laying of 20mm dia HDPE pipe at Sadipur Mouza for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000300/2022-2023 | 2040/MAAD | 16/11/2022 | 31/12/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 4.63 | 4.62 | 99.83 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Laying of 75 mm, 90 mm dia uPVC Pipe line at East Janutola, Barkattabad, Rishipara, Dhanuk Para, SK. Para, Bridge Para for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000167/2022-2023 | 1180/MAAD | 13/06/2022 | 28/07/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 4.83 | 4.83 | 99.97 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Bangitola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000123/2022-2023 | 1024/MAAD | 12/05/2022 | 26/06/2022 | BENGAL ENGINEERING COMPANY | 10.05 | 9.32 | 92.73 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | SM/09657 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
Total | [13 empty] | 24039.26 | 102.56 | 0.43