## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Lakshmipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza-Panchanandapur) | Assistant Engineer-II | Junior Engineer-II | ORD/000339/2021-2022 | 1748/MAAD | 24/11/2021 | 23/01/2022 | MILLENNIUM ENTERPRISE | 37.54 | 37.52 | 99.95 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Laxmipur Water Supply Scheme (Mouza- Khanpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000124/2022-2023 | 1025/MAAD | 12/05/2022 | 26/06/2022 | BENGAL ENGINEERING COMPANY | 10.69 | 9.56 | 89.44 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Laxmighat Water Supply Scheme (Mouza- Lakhmighat) extra pipe line at Lakhmipur village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000295/2022-2023 | 2035/MAAD | 16/11/2022 | 31/12/2022 | ANJIMA CONSTRUCTION CO. | 8.3 | 7.77 | 93.6 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Laying of 160 mm dia UPVC Pipe line and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Michhutola, Bhagattola under Uttar Laxmipur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000453/2022-2023 | 328/MAAD | 21/02/2023 | 22/04/2023 | M/S BABLU ENTERPRISE, | 21.8 | 21.72 | 99.6 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Laying 63/75/90 mm dia loop Pipe line to connect Chowdhury para and Pichli village to provide sufficient drinking water though FHTC at Pichli Village and construction of approach road and boundary wall at reservoir site with allied work under Laxmighat W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000193/2022-2023 | 1404/MAAD | 26/07/2022 | 09/09/2022 | FUTURE | 15.68 | 14.25 | 90.91 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1337/MAAD | 18/07/2022 | 18/07/2022 | Resource Division | 12.3 | 0 | 0 | 0
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | SM/09658 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24029.55 | 90.82 | 0.38