## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) |  |  | ORD/000385/2021-2022 | 2040MAAD | 29/12/2021 | 29/12/2022 | NITAI PANDAY | 1.73 | 0 | 0 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Dullugram, Krishnapur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000110/2022-2023 | 1012/MAAD | 12/05/2022 | 11/07/2022 | M/S ALISA CONSTRUCTION | 50.82 | 0 | 0 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Alinagar) | Assistant Engineer-II | Junior Engineer-II | ORD/000329/2021-2022 | 1741/MAAD | 24/11/2021 | 23/01/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 73.99 | 0 | 0 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Laying of 75 mm dia uPVC Pipe line at Ghoshpara, Sardar Tola, Babu Tola and Momin Para for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000158/2022-2023 | 1171MAAD | 13/06/2022 | 28/07/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 3.66 | 0 | 0 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Laying of 20mm dia HDPE pipe at Alinagar Mouza for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000245/2022-2023 | 1823MAAD | 27/09/2022 | 11/11/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 6.35 | 0 | 0 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Laying of 20mm dia HDPE pipe at Jote Dhani, Jote Param, Nabinagar, Nurnagar Mouzas for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000246/2022-2023 | 1824/MAAD | 27/09/2022 | 11/11/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 6.56 | 0 | 0 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Khaltipur, Silampur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000111/2022-2023 | 1057/MAAD | 24/05/2022 | 23/07/2022 | M/S SABANA CONSTRUCTION | 39.06 | 0 | 0 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 1786/MAAD | 26/11/2021 | 26/11/2021 | Resource Division | 29.65 | 0 | 0 | 0
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2022-2023 | 1014/MAAD | 12/05/2022 | 11/07/2022 | M/S ALISA CONSTRUCTION | 82.2 | 0 | 0 | 15
Total | [13 empty] | 294.02 | 0 | 0