## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KuddibarMohonpur, Munshipara, ShyampurColoni, Madia of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000341/2021-2022 | 1750/MAAD | 24/11/2021 | 08/01/2022 | M/S N. N. ENTERPRISE | 11.76 | 11.17 | 94.95 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Madia Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000349/2021-2022 | 1761/MAAD | 24/11/2021 | 23/01/2022 | BHOLANATH CONSTRUCTION | 41.21 | 41.13 | 99.8 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kuddibari Mohonpur of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000357/2021-2022 | 1721/MAAD | 18/11/2021 | 18/12/2021 | M/S N. N. ENTERPRISE | 4.79 | 4.79 | 100 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Repairing & Laying of pipeline at Bhabanipur & Pirpur under Bhabanipur mouza in connection with Jal Jeevan Mission (JJM), Repairing of valve Chamber & other allied works at Milki Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I | Junior Engineer-IV | ORD/000275/2022-2023 | 1876/MAAD | 28/09/2022 | 12/11/2022 | M/S N. N. ENTERPRISE | 5.27 | 5.12 | 97.08 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Khaskol Chandipur & Bhabanipur Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000189/2022-2023 | 1400/MAAD | 26/07/2022 | 24/09/2022 | M/S N. N. ENTERPRISE | 27.51 | 25.07 | 91.14 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1339/MAAD | 18/07/2022 | 18/07/2022 | Resource Division | 12.3 | 0 | 0 | 0
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1701/MAAD | 21/09/2022 | 21/09/2022 | Resource Division | 1.23 | 0 | 0 | 0
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Laying of pipeline at Milki G.S. Colony & Bhabanipur in connection with Jal Jeevan Mission (JJM) to provide FHTC at Milki Distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000035/2023-2024 | 884/MAAD | 11/05/2023 | 10/07/2023 | M/S N. N. ENTERPRISE | 7.75 | 7.74 | 99.89 | 100
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | SM/09660 | Retrofitting | Laying UPVC pipe at Laxmighat Nagrai and adjoining villages for FHTC under Laxmighat Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000216/2024-2025 | 1477/MAAD | 03/09/2024 | 01/11/2024 | M/S MANDAL & SONS | 2.49 | 0.61 | 24.52 | 90
Total | [13 empty] | 24037.56 | 95.63 | 0.4