## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sherpur) | Assistant Engineer-II | Junior Engineer-II | ORD/000337/2021-2022 | 1746/MAAD | 24/11/2021 | 23/01/2022 | A. K. CONSTRUCTION | 43.13 | 42.12 | 97.68 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme (Mouza- Chirampur, Purba Chandpur, Dakshin Debipur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000048/2022-2023 | 822/MAAD | 28/04/2022 | 27/06/2022 | A. K. CONSTRUCTION | 80.44 | 73.9 | 91.87 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of uPVC Pipe line at Dandi Gram, Jafarabad for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000503/2021-2022 | 388/MAAD | 08/03/2022 | 22/04/2022 | A. K. CONSTRUCTION | 13.29 | 13.09 | 98.52 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Sherpur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000249/2022-2023 | 1827MAAD | 27/09/2022 | 11/11/2022 | A. K. CONSTRUCTION | 6.84 | 6.82 | 99.76 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Fatekhani for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000247/2022-2023 | 1825MAAD | 27/09/2022 | 11/11/2022 | A. K. CONSTRUCTION | 5.59 | 5.57 | 99.7 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000266/2022-2023 | 1868/MAAD | 28/09/2022 | 28/10/2022 | A. K. CONSTRUCTION | 4.87 | 4.85 | 99.65 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000248/2022-2023 | 1826/MAAD | 27/09/2022 | 11/11/2022 | A. K. CONSTRUCTION | 5.19 | 5.17 | 99.66 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1702/MAAD | 21/09/2022 | 21/09/2022 | Resource Division | 4.93 | 0 | 0 | 0
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09661 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
Total | [13 empty] | 24087.51 | 151.53 | 0.63