## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000382/2021-2022 | 1788/MAAD | 26/11/2021 | 27/11/2021 | RESOURCE DIVISION, P.H.E. DTE. | 142 | 14.2 | 10 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Bagbari, Doulatpur) extra pipe line at Bagbari Bundh, Doulatpur and Ganipur at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000187/2022-2023 | 1398/MAAD | 26/07/2022 | 24/09/2022 | SOVON KUMAR DAS | 42.88 | 35.56 | 82.94 | 82
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying 63/75 mm dia Pipe at Basakpara village near Ashoke Basak house to Ramlal Chowdhury house, Protap Basak house to Shyamal Ghosh house, Sita Basak house to Ananda Basak house, Gopal Chowdhury house to Gopesh Rajak house, Suku paul house to Bijoy Mandal, Ramesh Mandal house to Sanjay Basak under Doulatpur W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte | Assistant Engineer-I | Junior Engineer-IV | ORD/000208/2022-2023 | 1456/MAAD | 29/07/2022 | 12/09/2022 | MAA MANASHA CONSTRUCTION | 1.68 | 1.67 | 99.86 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanpur , Bagbari, Laxmipur, Doulatpur Mouza of Doulatpur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000340/2021-2022 | 1749/MAAD | 24/11/2021 | 23/01/2022 | SOVON KUMAR DAS | 44.81 | 43.54 | 97.16 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying UPVC pipe at Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000322/2022-2023 | 2244/MAAD | 22/12/2022 | 05/02/2023 | SOVON KUMAR DAS | 19.89 | 19.26 | 96.85 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying UPVC pipe from PW Roads Towards Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000321/2022-2023 | 2243/MAAD | 22/12/2022 | 05/02/2023 | M/S AMIT KUMAR GUPTA | 13.95 | 13.78 | 98.74 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying of 20mm dia extra HDPE pipe at Bagbari, Doulatpur mouza for installation of FHTC under Doulatpur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000262/2022-2023 | 1864/MAAD | 28/09/2022 | 28/10/2022 | SOVON KUMAR DAS | 6.35 | 6.35 | 99.94 | 1
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 1788/MAAD | 26/11/2021 | 26/11/2021 | Resource Division | 56.12 | 0 | 0 | 0
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Laxmipur, Madhapur) at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000188/2022-2023 | 1399/MAAD | 26/07/2022 | 24/09/2022 | PARIJAT RAY | 33.54 | 28.41 | 84.73 | 75
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Chandipur) With pipe line at the same mouza Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000196/2022-2023 | 1534/MAAD | 05/08/2022 | 04/10/2022 | SAHA CONSTRUCTION | 34 | 33.81 | 99.45 | 100
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying UPVC pipe at Rajnagar Bagbari village & adjacent areas for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000387/2023-2024 | 307/MAAD | 11/03/2024 | 10/04/2024 | HIRAK ROYCHOUDHURY | 3.98 | 3.26 | 81.96 | 100
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying UPVC pipe at near Bagbari village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000385/2023-2024 | 305/MAAD | 11/03/2024 | 10/04/2024 | SR ENTERPRISE | 3.74 | 3.39 | 90.48 | 100
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
14 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | SM/09662 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bagbari and adjoining villages under command area of Doulatpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000382/2023-2024 | 302/MAAD | 11/03/2024 | 10/04/2024 | M/S MAA TARA ENTERPRISE | 8.77 | 6.49 | 74.06 | 80
Total | [13 empty] | 24334.94 | 209.73 | 0.86