## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Improvement of existing water supply pipe line of Nurpur, Tiarpara, Shamlalpara of Biswambhar Binodpur Distribution zone under Malda Arsenic Area W/S Division, PHE Dte. |  |  | ORD/000334/2020-2021 | 511/MAAD | 10/06/2020 | 10/06/2020 | KRISHNENDU DUTTA | 15.35 | 13.37 | 87.12 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nurpur Mouza of Biswambhar Binodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000347/2021-2022 | 1753/MAAD | 24/11/2021 | 23/01/2022 | NEOGI ENTERPRISE | 44.84 | 42.69 | 95.2 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kashimnagar Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000346/2021-2022 | 1759/MAAD | 24/11/2021 | 08/01/2022 | ABANI BHUSAN GHOSH | 31.2 | 31.04 | 99.48 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalbathani, KanshaBinodpur, Niranjanpur Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000348/2021-2022 | 1760/MAAD | 24/11/2021 | 23/01/2022 | M/S. JHA CONSTRUCTION | 55.62 | 36.81 | 66.19 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Nurpur Mouza ( Dallu tola, Pyas Tola, Mandal Tola) of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2022-2023 | 1403/MAAD | 26/07/2022 | 09/09/2022 | ABANI BHUSAN GHOSH | 24.12 | 24.11 | 99.98 | 1
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Kangso Binodpur, Madhupur, Lalbathani of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) . | Assistant Engineer-I | Junior Engineer-IV | ORD/000169/2022-2023 | 1182/MAAD | 13/06/2022 | 28/07/2022 | M/S. JHA CONSTRUCTION | 3.38 | 3.34 | 98.79 | 1
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Laying of HDPE pipe 20mm dia at Kashimnagar Mouza under Biswambhar Binodpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000031/2023-2024 | 854/MAAD | 03/05/2023 | 18/05/2023 | ABANI BHUSAN GHOSH | 4.58 | 4.58 | 100 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Laying UPVC pipe line and Providing FHTC at Harekrishna Kongar Colony and Kanchantar Binod nagar para under Boro Fulbaria W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000052/2023-2024 | 951/MAAD | 23/05/2023 | 07/07/2023 | TWO BROTHERS CONSTRUCTION | 4.63 | 4.16 | 89.85 | 100
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | SM/09663 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24106.96 | 160.11 | 0.66