## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) | SM/10202 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 332/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 50.25 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) | SM/10202 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-IV | ORD/000020/2022-2023 | 660/MAAD | 01/04/2022 | 16/09/2024 | MERCURY ENGINEERING COMPANY | 70.55 | 0 | 0 | 37
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) | SM/10202 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-IV | ORD/000011/2022-2023 | 658/MAAD | 01/04/2022 | 30/07/2022 | HANNAN BUILDERS PVT. LTD. | 84.7 | 47.48 | 56.06 | 90
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) | SM/10202 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-IV | ORD/000019/2022-2023 | 659/MAAD | 01/04/2022 | 01/01/2025 | MERCURY ENGINEERING COMPANY | 70.55 | 0 | 0 | 70
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) | SM/10202 | Anganwadi | Formal work order for Providing Drinking Water Supply in 45 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-V ) | Assistant Engineer-I | Junior Engineer-IV | ORD/000128/2022-2023 | 1075/MAAD | 01/06/2022 | 26/10/2024 | MERCURY ENGINEERING COMPANY | 319.24 | 0 | 0 | 90
Total | [13 empty] | 595.29 | 47.48 | 7.98