## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000025/2022-2023 | 835/MAAD | 28/04/2022 | 26/08/2022 | M/S S.S. ENTERPRISE | 157.47 | 151.25 | 96.05 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Kaliachak -II Block (Phase -I) under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000305/2022-2023 | 2043/MAAD | 16/11/2022 | 01/12/2022 | M/S S.S. ENTERPRISE | 23.55 | 23.55 | 100 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Formal work order for Providing Drinking Water Supply in 17 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak ¿ II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000026/2022-2023 | 948/MAAD | 11/05/2022 | 08/09/2022 | MILLENNIUM ENTERPRISE | 107.08 | 102.38 | 95.61 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Providing Drinking Water Supply in 15 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak -II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000002/2022-2023 | 640/MAAD | 01/04/2022 | 30/07/2022 | MILLENNIUM ENTERPRISE | 94.48 | 90.76 | 96.06 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 338/MAAD | 28/02/2022 |  | Resource Division | 39.61 | 0 | 0 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) | SM/10204 | School | Formal work order for Providing Drinking Water Supply in 47 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | Assistant Engineer-II | Junior Engineer-II | ORD/000127/2022-2023 | 1071/MAAD | 30/05/2022 | 28/08/2022 | M/S S.S. ENTERPRISE | 297.8 | 110.26 | 37.02 | 100
Total | [13 empty] | 720 | 478.21 | 66.42