## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Kaliachak -III Block under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000107/2022-2023 | 1030/MAAD | 12/05/2022 | 22/05/2022 | FUTURE | 5 | 5 | 100 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Continuation work order for Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Kaliachak - III Block under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000284/2022-2023 | 1611/MAAD | 01/09/2022 | 11/09/2022 | FUTURE | 4.39 | 4.39 | 100 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Formal work order for Providing Drinking Water Supply in 24 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000028/2022-2023 | 1055/MAAD | 24/05/2022 | 21/09/2022 | MOTI RAHAMAN | 150.74 | 144.23 | 95.69 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 337/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 76.19 | 0 | 0 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Formal work order for Providing Drinking Water Supply in 30 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak ¿ III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000027/2022-2023 | 779/MAAD | 22/04/2022 | 20/08/2022 | DEBAPRIYA SAHA | 188.97 | 179.89 | 95.2 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) | SM/10205 | School | Providing Drinking Water Supply in 15 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000003/2022-2023 | 641/MAAD | 01/04/2022 | 30/07/2022 | DEBAPRIYA SAHA | 94.48 | 89.28 | 94.49 | 100
Total | [13 empty] | 519.77 | 422.79 | 81.34