## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Providing Drinking Water Supply in 4 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000129/2022-2023 | 1129/MAAD | 10/06/2022 | 08/10/2022 | M/S. JHA CONSTRUCTION | 25.21 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Formal work order for Providing Drinking Water Supply in 30 Nos Source Less School Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | Assistant Engineer-II | Junior Engineer-II | ORD/000024/2022-2023 | 786/MAAD | 26/04/2022 | 24/08/2022 | USHA ENTERPRISE | 189.14 | 0 | 0 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Providing Drinking Water Supply in 4 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000130/2022-2023 | 1130/MD | 10/06/2022 | 08/10/2022 | M/S AMIT KUMAR GUPTA | 25.21 | 0 | 0 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000001/2022-2023 | 639/MAAD | 01/04/2022 | 30/07/2022 | BANIK BROTHERS | 63.04 | 0 | 0 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply inSource Less Schools & ICDS at Kaliachak -I Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000271/2022-2023 | 1900/MAAD | 13/10/2022 | 28/10/2022 | MERCURY ENGINEERING COMPANY | 11.91 | 0 | 0 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 336/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 4.46 | 0 | 0 | 0
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10206 | School | Providing Drinking Water Supply in 2 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000131/2022-2023 | 1131/MAAD | 10/06/2022 | 01/04/2025 | M/S PARIMAL DAS | 12.55 | 0 | 0 | 48
Total | [13 empty] | 331.52 | 0 | 0