## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Providing Drinking Water Supply in 6 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000023/2022-2023 | 654/MAAD | 01/04/2022 | 30/07/2022 | BANIK BROTHERS | 42.34 | 40.12 | 94.75 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000009/2022-2023 | 651/MAAD | 01/04/2022 | 30/07/2022 | HANNAN BUILDERS PVT. LTD. | 84.7 | 82.52 | 97.43 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000016/2022-2023 | 653/MAAD | 01/04/2022 | 30/07/2022 | M/S DAS CONSTRUCTION | 70.55 | 34.06 | 48.28 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000038/2022-2023 | 1056/MAAD | 24/05/2022 | 21/09/2022 | MOTI RAHAMAN | 175.68 | 169.8 | 96.65 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Kaliachak -III Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000313/2022-2023 | 2044/MAAD | 16/11/2022 | 01/12/2022 | DIPAYAN DEY | 24 | 24 | 100 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 329/MAAD | 28/02/2022 |  | Resource Division | 64.54 | 0 | 0 | 0
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) | SM/10234 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-III | ORD/000010/2022-2023 | 652/MAAD | 01/04/2022 | 30/07/2022 | MERCURY ENGINEERING COMPANY | 84.66 | 67.21 | 79.39 | 100
Total | [13 empty] | 546.48 | 417.71 | 76.44