## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) | SM/10236 | Anganwadi | Providing Drinking Water Supply in 6 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000125/2022-2023 | 1067/MAAD | 27/05/2022 | 24/09/2022 | M/S. JHA CONSTRUCTION | 42.35 | 40.73 | 96.17 | 100
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) | SM/10236 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 331/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 52.84 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) | SM/10236 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000008/2022-2023 | 646/MAAD | 01/04/2022 | 30/07/2022 | MILLENNIUM ENTERPRISE | 84.62 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) | SM/10236 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-II | ORD/000013/2022-2023 | 647/MAAD | 01/04/2022 | 30/07/2022 | MILLENNIUM ENTERPRISE | 70.52 | 0 | 0 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) | SM/10236 | Anganwadi | Formal work order for Providing Drinking Water Supply in 43 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-l ) | Assistant Engineer-II | Junior Engineer-II | ORD/000030/2022-2023 | 777/MAAD | 22/04/2022 | 21/07/2022 | MAMATA USHA ENTERPRISE | 305.05 | 206.61 | 67.73 | 80
Total | [13 empty] | 555.38 | 247.34 | 44.54