## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Providing Drinking Water Supply in 7 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure) | Assistant Engineer-I | Junior Engineer-I | ORD/000021/2022-2023 | 657/MAAD | 01/04/2022 | 30/07/2022 | BANIK BROTHERS | 49.4 | 47.75 | 96.66 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Formal work order for Providing Drinking Water Supply in 15 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000040/2022-2023 | 1050/MAAD | 23/05/2022 | 20/09/2022 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 105.78 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less ICDS at Manikchak Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000308/2022-2023 | 2051/MAAD | 18/11/2022 | 03/12/2022 | MERCURY ENGINEERING COMPANY | 10.17 | 10.17 | 100 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Manikchak Block (Phase -II ) under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000423/2022-2023 | 320/MAAD | 21/02/2023 | 08/03/2023 | M/S TRILOCHAN CONSTRUCTION CO. | 2.61 | 1.1 | 42.11 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 333/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 61.62 | 0 | 0 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000039/2022-2023 | 783/MAAD | 26/04/2022 | 24/08/2022 | NEOGI ENTERPRISE | 176.42 | 86.01 | 48.75 | 43
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000018/2022-2023 | 656/MAAD | 01/04/2022 | 30/07/2022 | MILLENNIUM ENTERPRISE | 70.52 | 54.72 | 77.6 | 65
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schools & ICDS at Manikchak Block (Phase -III) under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000422/2022-2023 | 319/MAAD | 21/02/2023 | 08/03/2023 | M/S TAPAS KUMAR CHAKRABORTY | 1.65 | 1.65 | 100 | 100
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10237 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | Assistant Engineer-II | Junior Engineer-I | ORD/000017/2022-2023 | 655/MAAD | 01/04/2022 | 30/07/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 70.31 | 67.97 | 96.67 | 6
Total | [13 empty] | 548.46 | 269.36 | 49.11