## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Manikchak Block under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000109/2022-2023 | 1032/MAAD | 12/05/2022 | 22/05/2022 | RAMASISH ENTERPRISE | 5 | 5 | 100 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000006/2022-2023 | 643/MAAD | 01/04/2022 | 30/07/2022 | BANIK BROTHERS | 63.04 | 59.63 | 94.59 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000005/2022-2023 | 642/MAAD | 01/04/2022 | 30/07/2022 | M/S TRILOCHAN CONSTRUCTION CO. | 62.67 | 59.5 | 94.93 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Formal Work order for Providing Drinking Water Supply in 21 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | Assistant Engineer-I | Junior Engineer-I | ORD/000034/2022-2023 | 781/MAAD | 26/04/2022 | 24/08/2022 | USHA ENTERPRISE | 132.38 | 125.02 | 94.44 | 95
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 335/MAAD | 28/02/2022 | 28/02/2022 | Resource Division | 44.07 | 0 | 0 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Formal work order for Providing Drinking Water Supply in 30 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2022-2023 | 778/MAAD | 22/04/2022 | 20/08/2022 | HANNAN BUILDERS PVT. LTD. | 189.14 | 181.43 | 95.93 | 61
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Formal work order for Providing Drinking Water Supply in 47 nos. Source Less School Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-l ) | Assistant Engineer-I | Junior Engineer-I | ORD/000046/2022-2023 | 1052/MAAD | 23/05/2022 | 21/08/2022 | M/S TAPAS KUMAR CHAKRABORTY | 297.8 | 248.07 | 83.3 | 82
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda | SM/10238 | School | Supply & delyvery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols at Manikchak Block (Phase-I) under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000279/2022-2023 | 1880/MAAD | 28/09/2022 | 13/10/2022 | M/S TAPAS KUMAR CHAKRABORTY | 4.76 | 0 | 0 | 75
Total | [13 empty] | 798.87 | 678.65 | 84.95