## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/10430 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2022-2023 | 1014/MAAD | 12/05/2022 | 11/07/2022 | M/S ALISA CONSTRUCTION | 82.2 | 0 | 0 | 15
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/10430 | Retrofitting | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2023 to 31.12.2023)= 365 days | Assistant Engineer-I | Junior Engineer-I | ORD/000404/2022-2023 | 2330/MAAD | 28/12/2022 | 28/12/2023 | NITAI PANDEY | 1.73 | 0 | 0 | 25
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/10430 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Godhan tola to Munnatola at Kumbhira Piped Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000037/2023-2024 | 885/MAAD | 11/05/2023 | 01/05/2025 | M/S AMIT KUMAR GUPTA | 34.21 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/10430 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 24041.38 | 0 | 0