## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur, Nagrai and adjoining villages under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000219/2024-2025 | 1480/MAAD | 03/09/2024 | 02/11/2024 | S. N. CONSTRUCTION | 7.08 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Milki G.S. Colony under command area of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000383/2023-2024 | 303/MAAD | 11/03/2024 | 10/04/2024 | M/S N. N. ENTERPRISE | 4.2 | 0 | 0 | 90
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11911 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 01/01/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000220/2024-2025 | 1481/MAAD | 03/09/2024 | 02/08/2025 | FUTURE | 7.08 | 0 | 0 | 0
Total | [13 empty] | 23941.6 | 0 | 0