## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Karmakarpara under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000270/2023-2024 | 3071/MAAD | 14/12/2023 | 12/02/2024 | DEY CONSTRUCTIONS | 9.92 | 0 | 0 | 100
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Nayagram (Baishnabnagar) under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000269/2023-2024 | 3070/MAAD | 14/12/2023 | 12/02/2024 | UNITED FRIENDS UMEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD | 4.97 | 0 | 0 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) from 17 mile bandh to Kamartola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000272/2023-2024 | 3072/MAAD | 14/12/2023 | 12/02/2024 | MD. TALEB ALI | 16.82 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 125 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) from Old 18 mile to Chamagram, Chhoto chamagram, Poladtola, Ajimtola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000275/2023-2024 | 3075/MAAD | 14/12/2023 | 01/03/2025 | ACHARYYA CONSTRUCTION | 29.1 | 0 | 0 | 100
Total | [13 empty] | 23984.06 | 0 | 0