## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11914 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 60
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11914 | Retrofitting | Sinking of 150mm. big dia. Tube Well of 60 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Jote Gopal Kagmari Distribution Zone (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000129/2024-2025 | 1260/MAAD | 24/06/2024 | 24/07/2024 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.79 | 4.63 | 96.64 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11914 | Retrofitting | Laying of 160 mm dia Pipeline at Sabjipara, Laying of rising main at Head work site and road restoration due to laying of pipe line at Chabilpara, Ailpara, Jote Daman under Jote Gopal Kagmari distribution Zone of Northern Sector under Malda Arsenic Area W/S Division, P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000122/2024-2025 | 1253/MAAD | 24/06/2024 | 24/07/2024 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.36 | 0 | 0 | 100
Total | [13 empty] | 23934.39 | 4.63 | 0.02