## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11915 | Retrofitting | Laying of 110 mm dia & 90 mm dia UPVC pipe, Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Kathalbari village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000127/2024-2025 | 1258/MAAD | 24/06/2024 | 01/04/2025 | SAHA CONSTRUCTION | 34.89 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11915 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Lalutola,Khublaltola & Gosaitola village under Charianantapur pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000126/2024-2025 | 1257/MAAD | 24/06/2024 | 24/07/2024 | MAHA MAYA CONSTRUCTION | 6.8 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11915 | Retrofitting | Laying of UPVC pipe 160mm dia & DI pipe 250 mm dia From Dariapur WTP (Back wash OHR) to 16 mile & others Allied works of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000222/2023-2024 | 1711/MAAD | 20/09/2023 | 19/12/2023 | S. R. CONSTRUCTION | 22.28 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11915 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
Total | [13 empty] | 23987.21 | 0 | 0