## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Akandabaria,Chakdomai & Umakantatola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000064/2022-2023 | 915/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.71 | 4.7 | 99.79 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Kalinagar, Malatipur & Zolatuli under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000065/2022-2023 | 916/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.67 | 4.66 | 99.74 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Saharatola, Golabari & Bhagabanpur under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dt | Assistant Engineer-II | Junior Engineer-III | ORD/000066/2022-2023 | 917/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.74 | 4.73 | 99.83 | 1
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Chakkupara, Nandalalpur & Agnutola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000067/2022-2023 | 918/MAAD | 10/05/2022 | 25/05/2022 | BANIK BROTHERS | 4.81 | 4.8 | 99.8 | 1
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of UVC pipe 200mm,90 mm dia at Kumvira to Nurnagar,Godhantola to munnatola & others Allied works to faciliate of house connection at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000001/2023-2024 | 622/MAAD | 05/04/2023 | 04/06/2023 | MI CONSTRUCTION | 22.74 | 22.58 | 99.27 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Repair & renovation of CI /DI Clear water main (Group-I) 750mm,700 mm,500 mm,450 mm,300 mm,250 mm) pipeline at diferrence places (Kaliachak band,Kaliachak PWD,Kaliachak Suraj Grill factory,jalalpur,Majompur bridge &Bholaichak) under Southern Sector under Malda Arsenic Area W/S Divn.PHE. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000040/2023-2024 | 855/MAAD | 03/05/2023 | 02/06/2023 | BANIK BROTHERS | 3.33 | 3.32 | 99.69 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of UPVC pipe 225mm,90 mm dia at Mohanpur ,Neoginagar & others Allied works at Kumvira W/S scheme at Kaliachak -III Block under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000049/2023-2024 | 948/MAAD | 23/05/2023 | 07/07/2023 | M/S SUBHASIS BHADURI | 8.83 | 7.91 | 89.52 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of UPVC pipe 225mm dia at Neogi nagar & others Allied works at Kumvira W/S scheme at Kaliachak-III Block under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000050/2023-2024 | 949/MAAD | 23/05/2023 | 07/07/2023 | SURAJIT MANDAL | 8.61 | 7.78 | 90.4 | 100
9 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Sardah, Naldahari, Chaitanna Tola & Nowda under Bholaichak water supply Zone of Southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000039/2023-2024 | 853/MAAD | 03/05/2023 | 18/05/2023 | BANIK BROTHERS | 8.37 | 8.36 | 99.98 | 100
10 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Kumbhira to Nurnagar at Kumbhira Piped Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000038/2023-2024 | 886/MAAD | 11/05/2023 | 10/07/2023 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.78 | 0 | 0 | 40
11 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of UPVC pipe line & Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Khuplaltola, Gosaitola under command area of Charianantapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000238/2023-2024 | 1892/MAAD | 12/10/2023 | 11/11/2023 | ABHIJIT CONSTRUCTION | 9.28 | 3.8 | 40.92 | 100
12 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Satangapara (Kashipara) & Sammohammadtola under Dariapur water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000271/2023-2024 | 3078/MAAD | 14/12/2023 | 12/02/2024 | M/S EHAN ENTERPRISE | 9.86 | 4.68 | 47.5 | 100
13 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | SM/11916 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 04/02/2025 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 20
Total | [13 empty] | 24051.98 | 77.32 | 0.32