## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Continuation work order for Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000286/2022-2023 | 1669/MAAD | 12/09/2022 | 22/09/2022 | FUTURE | 0.99 | 0.99 | 100 | 1
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2022-2023 | 1658/MAAD | 08/09/2022 | 18/09/2022 | FUTURE | 0.99 | 0.99 | 100 | 1
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Kadamtala Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000363/2022-2023 | 125/MAAD | 31/01/2023 | 17/03/2023 | JOY GURU ENTERPRISE | 14.57 | 5.52 | 37.88 | 100
4 | MALDAH | Kaliachak-I | Malda Mechanical | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Kadamtola, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001624/2023-2024 | 3004459313 | 11/10/2023 | 09/01/2024 | W.B.S.E.D.C.LTD | 4.14 | 4.14 | 100 | 100
5 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 632/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 1.06 | 0 | 0 | 0
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Construction of 300 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (3rd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000255/2023-2024 | 1920/MAAD | 16/10/2023 | 12/07/2024 | MD. TALEB ALI | 126.12 | 64.04 | 50.78 | 85
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Laying of Distribution System for Kadamtala Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000374/2022-2023 | 221/MAAD | 03/02/2023 | 04/05/2023 | M/S. JHA CONSTRUCTION | 71 | 67.98 | 95.75 | 90
8 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Kadamtala Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000060/2023-2024 | 983/MAAD | 06/06/2023 | 01/04/2025 | DIPAYAN DEY | 139.41 | 18.83 | 13.5 | 75
9 | MALDAH | Kaliachak-I | Malda Mechanical | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Kadamtala Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/014767) | Assistant Engineer - II | Junior Engineer-03 | ORD/000306/2023-2024 | 2265/MLMD | 18/07/2023 | 26/06/2026 | DEY ENTERPRISE.. | 54.08 | 40.4 | 74.7 | 48
10 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | SM/12708 | New | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000250/2024-2025 | 12/MAAD | 03/01/2025 | 04/03/2025 | M/S. JHA CONSTRUCTION | 52.96 | 0 | 0 | 0
Total | [13 empty] | 465.33 | 202.89 | 43.6