## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Continuation work order for Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000287/2022-2023 | 1671/MAAD | 12/09/2022 | 22/09/2022 | FUTURE | 0.99 | 0.99 | 100 | 1
2 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000232/2022-2023 | 1667/MAAD | 08/09/2022 | 18/09/2022 | FUTURE | 0.99 | 0.99 | 100 | 1
3 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Hamidpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000005/2023-2024 | 661/MAAD | 06/04/2023 | 21/05/2023 | JOY GURU ENTERPRISE | 14.6 | 10.79 | 73.88 | 100
4 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 624/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 10.54 | 0 | 0 | 0
5 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Laying of Distribution System at Paschim Tofi, Purba Tofi, Chumki Tola for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer-II | Junior Engineer-II | ORD/000006/2023-2024 | 677/MAAD | 12/04/2023 | 11/07/2023 | MD. TALEB ALI | 66.48 | 47.01 | 70.71 | 90
6 | MALDAH | Kaliachak-II | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Humidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - II | Junior Engineer-03 | ORD/001732/2023-2024 | 3390/MLMD | 31/10/2023 | 28/12/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.15 | 40.3 | 64.84 | 30
7 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Hamidpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000243/2024-2025 | 1697/MAAD | 19/11/2024 | 18/01/2025 | M/S MANDAL & SONS | 64 | 0 | 0 | 0
8 | MALDAH | Kaliachak-II | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000069/2024-2025 | 1650/MLMD | 25/06/2024 | 26/08/2024 | NITAI PANDEY | 0.78 | 0.77 | 99.22 | 0
9 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Laying of Distribution System at Nutun Tofi, Jalimtola, Sripur Colony, Sripur, Bakhrabaj ,for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000026/2023-2024 | 836/MAAD | 02/05/2023 | 29/02/2024 | M/S MOON LIGHT CONSTRUCTION & CO. | 46.85 | 35.22 | 75.18 | 100
10 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2ND Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000103/2023-2024 | 1411/MAAD | 20/07/2023 | 01/07/2025 | WIST WATER SOLUTIONS PRIVATE LIMITED | 156.58 | 0 | 0 | 15
11 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Hamidpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000104/2023-2024 | 1409/MAAD | 20/07/2023 | 01/04/2024 | M. I. CONSTRUCTION | 4.96 | 0 | 0 | 100
12 | MALDAH | Kaliachak-II | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Quotation Payment againsts Hamidpur PH NO 1 Under Mothabri CCC Under the district of Malda |  |  | BILL/03201/2024-2025 |  | 20/01/2025 | 20/01/2025 | W.B.S.E.D.C.LTD | 8.63 | 0 | 0 | 0
13 | MALDAH | Kaliachak-II | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Quotation Payment for Hamidpur PH NO 2 Under Mothabari CCC Under the district of MALDA |  |  | BILL/02732/2024-2025 | BP-2024-25-622 | 09/01/2025 | 09/01/2025 | W.B.S.E.D.C.LTD | 7.36 | 0 | 0 | 0
14 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | SM/12709 | New | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Hamidpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000219/2023-2024 | 1707/MAAD | 20/09/2023 | 31/12/2024 | M/S MOON LIGHT CONSTRUCTION & CO. | 203.55 | 72.68 | 35.7 | 80
Total | [13 empty] | 648.44 | 208.75 | 32.19