## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2022-2023 | 1666/MAAD | 08/09/2022 | 18/09/2022 | FUTURE | 0.99 | 0 | 0 | 1
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Continuation work order for Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000288/2022-2023 | 1670/MAAD | 12/09/2022 | 22/09/2022 | FUTURE | 0.99 | 0 | 0 | 1
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mosimpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000364/2022-2023 | 155/MAAD | 02/02/2023 | 19/03/2023 | A ONE ENTERPRISE | 14.72 | 0 | 0 | 100
4 | MALDAH | Kaliachak-I | Malda Mechanical | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000770/2023-2024 | 3004390333 | 10/08/2023 | 08/11/2023 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0 | 100
5 | MALDAH | Kaliachak-I | Malda Mechanical | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000769/2023-2024 | 3004395276 | 16/08/2023 | 14/11/2023 | W.B.S.E.D.C.LTD | 5.97 | 0 | 0 | 100
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 623/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 21.69 | 0 | 0 | 0
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer-II | Junior Engineer-II | ORD/000450/2022-2023 | 399/MAAD | 06/03/2023 | 01/08/2024 | MANIK CHOUDHURY | 70.26 | 0 | 0 | 80
8 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Laying of Distribution System at Mosimpur Chama Para, Beltala, Biswas Para, Darga Para, Khursed Para, Wayesh Mistry Para, Balupur, Baliharpur Rilif Pukur Para for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000375/2022-2023 | 222/MAAD | 03/02/2023 | 01/04/2025 | SAHA CONSTRUCTION | 33.71 | 0 | 0 | 95
9 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer-II | Junior Engineer-II | ORD/000377/2023-2024 | 222/MAAD | 27/02/2024 | 27/05/2024 | MANIK CHOUDHURY | 3.73 | 0 | 0 | 90
10 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mosimpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000365/2022-2023 | 108/MAAD | 30/01/2023 | 31/03/2023 | MD WARESH ALI | 5.02 | 0 | 0 | 100
11 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000021/2023-2024 | 857/MAAD | 03/05/2023 | 01/04/2025 | USHA ENTERPRISE | 168.7 | 0 | 0 | 85
12 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000217/2023-2024 | 1705/MAAD | 20/09/2023 | 01/07/2025 | A. K. CONSTRUCTION | 211.7 | 0 | 0 | 80
13 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | SM/13451 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000252/2024-2025 | 13/MAAD | 03/01/2025 | 22/02/2025 | A. K. CONSTRUCTION | 66.36 | 0 | 0 | 90
Total | [13 empty] | 607 | 0 | 0