## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Muslim Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000028/2023-2024 | 865/MAAD | 04/05/2023 | 03/07/2023 | ABHIJIT ENTERPRISE | 9.75 | 0 | 0 | 100
2 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 1st Tube well Site Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2023-2024 | 866/MAAD | 04/05/2023 | 18/06/2023 | M/S DYNAMIC CONSTRUCTION | 7.47 | 0 | 0 | 100
3 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 634/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 24.86 | 0 | 0 | 0
4 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Bazar Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000027/2023-2024 | 864/MAAD | 04/05/2023 | 03/07/2023 | CHARU CONSTRUCTION | 13.56 | 0 | 0 | 100
5 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 102 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Purbha Saidpur Piped Water supply scheme (2nd Tube Well Site) at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. (2nd call) | Assistant Engineer-I | Junior Engineer-I | ORD/000253/2023-2024 | 1916/MAAD | 16/10/2023 | 15/11/2023 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.2 | 0 | 0 | 100
6 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO 1 Under The District Of Malda Under Mathurapur CCC |  |  | BILL/00018/2024-2025 | BP-2024-25-43 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 5.08 | 0 | 0 | 0
7 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO II For district of Malda Under Mathurapur CCC |  |  | BILL/03761/2023-2024 | BP-2023-24-731 | 28/03/2024 | 28/03/2024 | W.B.S.E.D.C.LTD | 4.54 | 0 | 0 | 0
8 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Sahebnagar High School Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000034/2023-2024 | 883/MAAD | 11/05/2023 | 10/07/2023 | MD WARESH ALI | 19.28 | 0 | 0 | 55
9 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves from Node point at Bhakta Ballavpur (71) mouza under Purbba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd Call) | Assistant Engineer-I | Junior Engineer-I | ORD/000045/2023-2024 | 944/MAAD | 23/05/2023 | 22/07/2023 | ANJIMA CONSTRUCTION CO. | 25.48 | 0 | 0 | 50
10 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Purba Saidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018015) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000652/2023-2024 | 2684/MLMD | 11/08/2023 | 01/12/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 65.01 | 0 | 0 | 98
11 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme at Purba Saidpur Piped Water Supply Scheme & its adjoining mouzas of Manikchak Block in the District of Malda, under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000258/2023-2024 | 2002/MAAD | 06/11/2023 | 27/08/2025 | M/S KUNDU CONSTRUCTION | 187.22 | 0 | 0 | 20
12 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000267/2023-2024 | 3017/MAAD | 06/12/2023 | 01/10/2025 | ZEOLITE FRESH INDIA | 150.68 | 0 | 0 | 5
13 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Maszid Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000032/2023-2024 | 882/MAAD | 11/05/2023 | 04/03/2024 | SUDIP DEY | 53.75 | 0 | 0 | 10
14 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000139/2023-2024 | 1480/MAAD | 01/08/2023 | 30/09/2023 | MAHA MAYA CONSTRUCTION | 5.09 | 0 | 0 | 80
Total | [13 empty] | 577.96 | 0 | 0