## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Muslim Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000028/2023-2024 | 865/MAAD | 04/05/2023 | 03/07/2023 | ABHIJIT ENTERPRISE | 9.75 | 8.71 | 89.34 | 100
2 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 1st Tube well Site Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2023-2024 | 866/MAAD | 04/05/2023 | 18/06/2023 | M/S DYNAMIC CONSTRUCTION | 7.47 | 4.58 | 61.28 | 100
3 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 634/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 24.86 | 0 | 0 | 0
4 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves from Node point at Bhakta Ballavpur (71) mouza under Purbba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd Call) | Assistant Engineer-I | Junior Engineer-I | ORD/000045/2023-2024 | 944/MAAD | 23/05/2023 | 22/07/2023 | ANJIMA CONSTRUCTION CO. | 25.48 | 24.58 | 96.47 | 50
5 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Bazar Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000027/2023-2024 | 864/MAAD | 04/05/2023 | 03/07/2023 | CHARU CONSTRUCTION | 13.56 | 12.4 | 91.47 | 100
6 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 102 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Purbha Saidpur Piped Water supply scheme (2nd Tube Well Site) at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. (2nd call) | Assistant Engineer-I | Junior Engineer-I | ORD/000253/2023-2024 | 1916/MAAD | 16/10/2023 | 15/11/2023 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.2 | 5.78 | 93.18 | 100
7 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO 1 Under The District Of Malda Under Mathurapur CCC |  |  | BILL/00018/2024-2025 | BP-2024-25-43 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 5.08 | 0 | 0 | 0
8 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO II For district of Malda Under Mathurapur CCC |  |  | BILL/03761/2023-2024 | BP-2023-24-731 | 28/03/2024 | 28/03/2024 | W.B.S.E.D.C.LTD | 4.54 | 0 | 0 | 0
9 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Sahebnagar High School Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000034/2023-2024 | 883/MAAD | 11/05/2023 | 10/07/2023 | MD WARESH ALI | 19.28 | 10.51 | 54.5 | 55
10 | MALDAH | Manikchak | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Purba Saidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018015) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000652/2023-2024 | 2684/MLMD | 11/08/2023 | 01/12/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 65.01 | 31.01 | 47.7 | 98
11 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme at Purba Saidpur Piped Water Supply Scheme & its adjoining mouzas of Manikchak Block in the District of Malda, under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000258/2023-2024 | 2002/MAAD | 06/11/2023 | 27/08/2025 | M/S KUNDU CONSTRUCTION | 187.22 | 43.31 | 23.13 | 20
12 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000267/2023-2024 | 3017/MAAD | 06/12/2023 | 01/10/2025 | ZEOLITE FRESH INDIA | 150.68 | 24.86 | 16.5 | 5
13 | MALDAH | Manikchak | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | SM/15140 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site at Purba Saidpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000259/2024-2025 | 57/MAAD | 13/01/2025 | 12/02/2025 | FUTURE | 26.42 | 0 | 0 | 60
Total | [13 empty] | 545.54 | 165.73 | 30.38