## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Arapur Water Supply Scheme (Mouza- Jote, Arapur) extra pipe line at Ganipur, Jote and Ghoshpara village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000251/2022-2023 | 1829/MAAD | 27/09/2022 | 11/11/2022 | BANIK BROTHERS | 2.46 | 2.45 | 99.85 | 1
2 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Laying UPVC pipe at Ghoshpara village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000427/2022-2023 | 323/MAAD | 21/02/2023 | 22/04/2023 | M/S RADHA KRISHNA ENTERPRISE | 3.2 | 3.14 | 98.17 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Laying UPVC pipe at Arapur village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000426/2022-2023 | 322/MAAD | 21/02/2023 | 22/04/2023 | S. N. CONSTRUCTION | 8.05 | 7.98 | 99.12 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000428/2022-2023 | 324/MAAD | 21/02/2023 | 22/04/2023 | S. R. CONSTRUCTION | 8.42 | 6.25 | 74.19 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Source Augmentation of Arapur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda | Assistant Engineer-I | Junior Engineer-IV | ORD/000479/2022-2023 | 616/MAAD | 31/03/2023 | 15/05/2023 | M/S DYNAMIC CONSTRUCTION | 7.47 | 5.59 | 74.86 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Arapur , Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II |  | ORD/000865/2023-2024 | 3004409400 | 31/08/2023 | 29/11/2023 | W.B.S.E.D.C.LTD | 4.18 | 4.18 | 100 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1690/MAAD | 15/09/2023 | 15/09/2023 | Resource Division | 9.79 | 0 | 0 | 0
8 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Ghoshpara village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000429/2022-2023 | 325/MAAD | 21/02/2023 | 22/04/2023 | S. R. ENTERPRISE | 6.36 | 5.32 | 83.71 | 100
9 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Extension of Pipe line by different dia UPVC pipe for ARAPUR Water Supply Scheme of English Bazar Dev. Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000463/2022-2023 | 552/MAAD | 24/03/2023 | 23/05/2023 | ACHARYYA CONSTRUCTION | 18.74 | 16.8 | 89.61 | 100
10 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Construction of 3.60 mtr X 3.00 Mtr. Bore Hole pump house for Tube well no-3 at Arapur Water Supply Scheme of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000460/2022-2023 | 478/MAAD | 22/03/2023 | 21/05/2023 | GOALPARA CO OPTV LABOUR CONTRACT AND CONSTN COCIETY LIMITED | 5.32 | 4.66 | 87.72 | 100
11 | MALDAH |  | Malda Mechanical | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Souce augmentation of Arapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017481) | Assistant Engineer - II | Junior Engineer-03 | ORD/000562/2023-2024 | 2616/MLMD | 10/08/2023 | 06/02/2024 | S.G.ENTERPRISE | 11.52 | 11.49 | 99.81 | 100
12 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | SM/15141 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000381/2023-2024 | 301/MAAD | 11/03/2024 | 10/04/2024 | GIRIDHARI CONSTRUCTION | 7.9 | 7.67 | 97.01 | 100
Total | [13 empty] | 93.4 | 75.54 | 80.87