## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bholaichak ,Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000105/2023-2024 | 3004305025/quot/03 | 29/05/2023 | 27/08/2023 | W.B.S.E.D.C.LTD | 1.83 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Uttar Laxmipur,Southern Zone ,Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000106/2023-2024 | 3004298515/quot/03 | 19/05/2023 | 17/08/2023 | W.B.S.E.D.C.LTD | 1.83 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Alinagar ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000381/2022-2023 | 239/MAAD | 09/02/2023 | 10/05/2023 | M/S MOON LIGHT CONSTRUCTION & CO. | 32.97 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bholaichak ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000382/2022-2023 | 240/MAAD | 09/02/2023 | 10/05/2023 | FUTURE | 32.98 | 0 | 0 | 100
5 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of NARAYANPUR Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000291/2023-2024 | 3004364587 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.32 | 0 | 0 | 100
6 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Alinagar Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000304/2023-2024 | 3004365949 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 1.8 | 0 | 0 | 100
7 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge of Sattari Distribution Zone, Rathbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II |  | ORD/001532/2023-2024 | 3004371435 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 1.22 | 0 | 0 | 100
8 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Sattari ) Distribution Zone of Nothern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-IV | ORD/000385/2022-2023 | 242/MAAD | 09/02/2023 | 29/06/2024 | SUBHAS CHANDRA KESHARI | 32.99 | 0 | 0 | 70
9 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Sattari Distribution Zone within Malda Arsenic Area Water Supply Scheme (Northern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001157/2022-2023 | 540/MLMD | 22/03/2023 | 18/09/2023 | M/S P.P. ELECTRICALS | 62.79 | 0 | 0 | 96
10 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bamongram) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000376/2022-2023 | 268/MAAD | 15/02/2023 | 16/05/2023 | BEE GEE CONSTRUCTION | 29.06 | 0 | 0 | 100
11 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Narayanpur) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000383/2022-2023 | 241/MAAD | 09/02/2023 | 10/05/2023 | M/S PARIMAL DAS | 33.02 | 0 | 0 | 100
12 | MALDAH |  | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Uttar Laxmipur ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000384/2022-2023 | 243/MAAD | 09/02/2023 | 10/05/2023 | DISHERY ENGINEERS CO OP SOCIETY LTD. | 32.96 | 0 | 0 | 100
13 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Utar Laxmipur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-04 | ORD/001123/2022-2023 | 454/MLMD | 16/03/2023 | 12/09/2023 | EASTERN INDIA SALES & SERVICE. | 62.77 | 0 | 0 | 100
14 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Alinagar Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-04 | ORD/001156/2022-2023 | 539/MLMD | 22/03/2023 | 18/09/2023 | DEY ENTERPRISE [HOWRAH] | 62.34 | 0 | 0 | 100
15 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Bholaichak Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-03,Junior Engineer-04 | ORD/001155/2022-2023 | 538/MLMD | 22/03/2023 | 01/07/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION. | 61.76 | 0 | 0 | 96
16 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Bamangram Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-04 | ORD/001137/2022-2023 | 536/MLMD | 22/03/2023 | 18/09/2023 | DEY ENTERPRISE.. | 62.79 | 0 | 0 | 100
17 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Narayanpur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-04 | ORD/001138/2022-2023 | 537/MLMD | 22/03/2023 | 18/09/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.75 | 0 | 0 | 100
18 | MALDAH |  | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | SM/15142 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/003453/2023-2024 | 845/MLMD | 21/02/2024 | 22/04/2024 | NITAI PANDEY | 0.78 | 0 | 0 | 100
Total | [13 empty] | 580.95 | 0 | 0