## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 120 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000007/2023-2024 | 692/MAAD | 13/04/2023 | 28/05/2023 | M/S DYNAMIC CONSTRUCTION | 7.38 | 0 | 0 | 100
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Daibakipur, Uttar Nazirpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II |  | ORD/000861/2023-2024 | 3004409374 | 31/08/2023 | 29/11/2023 | W.B.S.E.D.C.LTD | 4.88 | 0 | 0 | 100
3 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Route servey & design for prepration of DPR of Uttar Nazirpur, Sakullapur & Nabinagar Piped Water Supply Scheme at Englishbazar & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000249/2023-2024 | 1763/MAAD | 30/09/2023 | 15/10/2023 | FUTURE | 0.99 | 0 | 0 | 100
4 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Laying of Distribution System and other allied works at Satichura in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000221/2023-2024 | 1710/MAAD | 20/09/2023 | 19/12/2023 | M/S. AYUSH BUILDERS | 11.67 | 0 | 0 | 75
5 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Laying of Distribution System and other allied works at Daibakipur & Paharipara in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000274/2023-2024 | 3074/MAAD | 14/12/2023 | 12/02/2024 | MAHA MAYA CONSTRUCTION | 16.89 | 0 | 0 | 85
6 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Construction of 5.40 mtr.X 3.6 mtr 3rd Pump House with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000008/2023-2024 | 691/MAAD | 13/04/2023 | 12/06/2023 | HIND CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 6.52 | 0 | 0 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Uttar Nazirpur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/017480) | Assistant Engineer - II | Junior Engineer-03 | ORD/000582/2023-2024 | 2631/MLMD | 10/08/2023 | 06/02/2024 | FUTURE | 10.51 | 0 | 0 | 80
8 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Uttar Nazirpur Water Supply Scheme (Augmentation) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000384/2023-2024 | 304/MAAD | 11/03/2024 | 10/04/2024 | PRITAM ENTERPRISE | 9.05 | 0 | 0 | 100
9 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 23.38 M³/ Hr. capacity Iron Elimination Plant (Pressure type) including construction of switch room in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme at English Bazar Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer-I | Junior Engineer-IV | ORD/000048/2023-2024 | 947/MAAD | 23/05/2023 | 13/11/2024 | SOVON KUMAR DAS | 15.66 | 0 | 0 | 100
10 | MALDAH |  | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | SM/15144 | Augmentation | Construction of Boundary Wall at 3rd Pump House Site, Laying of distribution system and providing FHTC of Uttar Nazirpur Distribution Zone at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000247/2024-2025 | 1700/MAAD | 19/11/2024 | 17/02/2025 | DEY CONSTRUCTION | 25.94 | 0 | 0 | 100
Total | [13 empty] | 109.49 | 0 | 0