## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15145 | Augmentation | Construction of Boundary wall including RBT fencing at arround Talimnagar Zone-I Pump house No.1 under Malda Arsenic Area Water supply Divisin PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000044/2023-2024 | 943/MAAD | 23/05/2023 | 07/07/2023 | MI CONSTRUCTION | 8.91 | 7.05 | 79.1 | 100
2 | MALDAH |  | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15145 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Talimnagar Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000451/2022-2023 | 400/MAAD | 06/03/2023 | 02/09/2023 | MANASH KUMAR SAHA | 16.01 | 6.51 | 40.65 | 81
Total | [13 empty] | 24.93 | 13.56 | 54.4