## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001901/2023-2024 | 3004364396 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 6.59 | 6.59 | 100 | 100
2 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001902/2023-2024 | 3004364409 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 5.14 | 5.14 | 100 | 100
3 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 630/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 166.19 | 0 | 0 | 0
4 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Laying of Distribution System & others allied works at Sukdevpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000058/2023-2024 | 967/MAAD | 31/05/2023 | 29/08/2023 | KRISHNENDU DUTTA | 49.45 | 0 | 0 | 0
5 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Head Work Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda(Kaliachak-III). (2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000055/2023-2024 | 964/MAAD | 31/05/2023 | 15/07/2023 | ASHIS CONSTRUCTION | 7.66 | 6.34 | 82.76 | 100
6 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 2nd Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda (Kaliachak-III). (2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2023-2024 | 965/MAAD | 31/05/2023 | 15/07/2023 | ABHIJIT PAUL | 7.65 | 5.78 | 75.58 | 100
7 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | ERECTION OF NEW HTOH LINE FOR SABDALPUR PH1 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT |  |  | BILL/03562/2023-2024 | BP-2023-24-588 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0 | 0
8 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | ERECTION OF HTOH FOR SABDALPUR PH 2 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT |  |  | BILL/03563/2023-2024 | BP-2023-24-587 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 2.45 | 0 | 0 | 0
9 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(Kaliachak-lll)(2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000022/2023-2024 | 984/MAAD | 06/06/2023 | 02/02/2025 | MOTI RAHAMAN | 168.03 | 0 | 0 | 55
10 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sabdalpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017775) | Assistant Engineer - II | Junior Engineer-03 | ORD/000658/2023-2024 | 2686/MLMD | 11/08/2023 | 07/02/2024 | DAS ENTERPRISE. | 76.87 | 0 | 0 | 20
11 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sabdulpur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000220/2023-2024 | 1708/MAAD | 20/09/2023 | 01/07/2025 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 222.96 | 40.85 | 18.32 | 65
12 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Laying of Distribution System & others allied works at Sabdalpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. (Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000225/2023-2024 | 1741/MAAD | 26/09/2023 | 01/03/2025 | M/S ALISA CONSTRUCTION | 64.67 | 44.17 | 68.3 | 15
13 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of Boundary Wall at Head Work Site,2nd tubewell site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission(JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Sabdulpur Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000253/2024-2025 | 14/MAAD | 03/01/2025 | 04/03/2025 | M/S AMIT KUMAR GUPTA | 89.63 | 0 | 0 | 0
Total | [13 empty] | 870.38 | 108.86 | 12.51