## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(Kaliachak-lll)(2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000022/2023-2024 | 984/MAAD | 06/06/2023 | 10/09/2025 | MOTI RAHAMAN | 168.03 | 0 | 0 | 55
2 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Laying of Distribution System & others allied works at Sukdevpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000058/2023-2024 | 967/MAAD | 31/05/2023 | 29/08/2023 | KRISHNENDU DUTTA | 49.45 | 0 | 0 | 0
3 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sabdalpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017775) | Assistant Engineer - II | Junior Engineer-03 | ORD/000658/2023-2024 | 2686/MLMD | 11/08/2023 | 06/01/2026 | DAS ENTERPRISE. | 76.87 | 0 | 0 | 20
4 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sabdulpur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000220/2023-2024 | 1708/MAAD | 20/09/2023 | 28/03/2026 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 222.96 | 40.85 | 18.32 | 65
5 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Laying of Distribution System & others allied works at Sabdalpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. (Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000225/2023-2024 | 1741/MAAD | 26/09/2023 | 01/03/2025 | M/S ALISA CONSTRUCTION | 64.67 | 44.17 | 68.3 | 15
6 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sabdulpur Piped Water Supply Scheme of Southern Sector under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda.(Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000057/2023-2024 | 966/MAAD | 31/05/2023 | 29/09/2024 | ABHIJIT CONSTRUCTION | 5 | 4 | 80.05 | 100
7 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 2nd Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda (Kaliachak-III). (2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2023-2024 | 965/MAAD | 31/05/2023 | 15/07/2023 | ABHIJIT PAUL | 7.65 | 5.78 | 75.58 | 100
8 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Head Work Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda(Kaliachak-III). (2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000055/2023-2024 | 964/MAAD | 31/05/2023 | 15/07/2023 | ASHIS CONSTRUCTION | 7.66 | 6.34 | 82.76 | 100
9 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001901/2023-2024 | 3004364396 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 6.59 | 6.59 | 100 | 100
10 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001902/2023-2024 | 3004364409 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 5.14 | 5.14 | 100 | 100
11 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 630/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 166.19 | 0 | 0 | 0
12 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | ERECTION OF HTOH FOR SABDALPUR PH 2 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT |  |  | BILL/03563/2023-2024 | BP-2023-24-587 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 2.45 | 0 | 0 | 0
13 | MALDAH | Kaliachak-III | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | ERECTION OF NEW HTOH LINE FOR SABDALPUR PH1 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT |  |  | BILL/03562/2023-2024 | BP-2023-24-588 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0 | 0
14 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15275 | New | Construction of Boundary Wall at Head Work Site,2nd tubewell site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission(JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Sabdulpur Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000253/2024-2025 | 14/MAAD | 03/01/2025 | 04/03/2025 | M/S AMIT KUMAR GUPTA | 89.63 | 0 | 0 | 0
Total | [13 empty] | 875.37 | 112.86 | 12.89