## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 666/MAAD | 11/04/2023 | 11/04/2023 | Resource Division | 25.35 | 0 | 0 | 0
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Construction of 900 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000033/2023-2024 | 868/MAAD | 04/05/2023 | 01/04/2025 | NEOGI ENTERPRISE | 364.29 | 67.4 | 18.5 | 80
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Laying of Distribution System for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000379/2023-2024 | 281/MAAD | 06/03/2024 | 04/06/2024 | SOFIQUL ISLAM | 166.6 | 32.41 | 19.45 | 30
4 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Sinking of Three nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Alipur Piped Water supply scheme (Head Work Site, 2nd Tube well site & 3rd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000262/2023-2024 | 2055/MAAD | 22/11/2023 | 06/01/2024 | M/S S.S. ENTERPRISE | 22.17 | 14.32 | 64.58 | 100
5 | MALDAH | Kaliachak-I | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I , II & III and Arsenic Iron Removal Plant at Alipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - II | Junior Engineer-03 | ORD/000737/2023-2024 | 2614/MLMD | 10/08/2023 | 28/05/2026 | DIPALI CONSTRUCTION. | 86.14 | 0 | 0 | 32
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000261/2023-2024 | 2058/MAAD | 22/11/2023 | 22/05/2025 | MERCURY ENGINEERING COMPANY | 271.74 | 0 | 0 | 10
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Construction of Boundary Wall at Head Work Site , 2nd Tube Well Site and 3rd Tube Well Site, Laying of rising main from 2nd and 3rd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000290/2024-2025 | 406/MAAD | 12/03/2025 | 10/06/2025 | NEOGI ENTERPRISE | 125.15 | 0 | 0 | 0
8 | MALDAH | Kaliachak-I | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/001770/2024-2025 | 4336/MLMD | 31/12/2024 | 28/02/2025 | SUBRATA SAHA | 0.77 | 0 | 0 | 0
9 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 3rd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000259/2023-2024 | 2056/MAAD | 22/11/2023 | 01/04/2024 | BINA CONSTRUCTION | 5.02 | 4.26 | 84.79 | 100
10 | MALDAH | Kaliachak-I | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Quotation Payment of ALIPUR T/W II for WBSEDCL Under Kaliachak CCC Under the district of MALDA |  |  | BILL/03525/2024-2025 | BP-2024-25-749 | 28/03/2025 | 28/03/2025 | W.B.S.E.D.C.LTD | 7.71 | 0 | 0 | 0
11 | MALDAH | Kaliachak-I | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Quotation Payment for ALIPUR T/W III Under Kaliachak CCC Under the district of Malda. |  |  | BILL/03526/2024-2025 | BP-2024-25-750 | 28/03/2025 | 28/03/2025 | W.B.S.E.D.C.LTD | 6.72 | 0 | 0 | 0
12 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | SM/15521 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000260/2023-2024 | 2057/MAAD | 22/11/2023 | 01/05/2024 | TARUN KANTI BAGCHI | 5.02 | 0 | 0 | 100
Total | [13 empty] | 1086.68 | 118.38 | 10.89