## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-III | Malda Mechanical | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Bakhrabad PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001908/2023-2024 | 3004379428 | 01/08/2023 | 30/10/2023 | W.B.S.E.D.C.LTD | 2.27 | 2.27 | 100 | 100
2 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 626/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 6.21 | 0 | 0 | 0
3 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Laying of Distribution System & others allied works at Kumbhira under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000135/2023-2024 | 1477/MAAD | 01/08/2023 | 01/08/2024 | S. R. CONSTRUCTION | 63.18 | 62.47 | 98.89 | 95
4 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Laying of Distribution System & others allied works at Char Bakrabad under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer-II | Junior Engineer-III | ORD/000134/2023-2024 | 1476/MAAD | 01/08/2023 | 30/09/2023 | DEY CONSTRUCTION | 65.47 | 58.13 | 88.78 | 80
5 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Bakhrabad Piped Water supply scheme of Kaliachak-III Block (Head work site) under Malda arsenic Area water supply Division in the disrtict of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2023-2024 | 1475/MAAD | 01/08/2023 | 15/09/2023 | MD. TALEB ALI | 7.65 | 4.92 | 64.27 | 100
6 | MALDAH | Kaliachak-III | Malda Mechanical | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Bakhrabad Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017774) | Assistant Engineer - II | Junior Engineer-03 | ORD/000663/2023-2024 | 2689/MLMD | 11/08/2023 | 27/07/2025 | GHOSH BROTHERS... | 49.58 | 0 | 0 | 0
7 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/15944 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Bakrabad Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000361/2023-2024 | 51/MAAD | 18/01/2024 | 01/08/2025 | WIST WATER SOLUTIONS PRIVATE LIMITED | 131.25 | 0 | 0 | 15
Total | [13 empty] | 325.61 | 127.79 | 39.24