## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Mechanical | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15946 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jotparan PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001013/2023-2024 | 3004427246 | 18/09/2023 | 17/12/2023 | W.B.S.E.D.C.LTD | 4.37 | 4.37 | 100 | 100
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15946 | New | Implementation of Jotparan Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000091/2023-2024 | 1388/MAAD | 14/07/2023 | 01/11/2024 | BANIK BROTHERS | 383.2 | 207.41 | 54.13 | 85
Total | [13 empty] | 387.57 | 211.78 | 54.64