## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Mechanical | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Gayeshbari Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018180) | Assistant Engineer - II |  | ORD/000656/2023-2024 | 2685/MLMD | 11/08/2023 | 07/02/2024 | SUNRISE ENGINEERING CORPORATION. | 63.77 | 0 | 0 | 0
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Laying of Distribution System including Supply of all type of specials & valves for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000276/2023-2024 | 3076/MAAD | 14/12/2023 | 01/07/2025 | FUTURE | 96.7 | 0 | 0 | 35
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Gayeshbari Piped Water supply scheme (Head Work Site & 2nd Tube Well Site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000137/2023-2024 | 1478/MAAD | 01/08/2023 | 15/09/2023 | ASHIS CONSTRUCTION | 14.64 | 9.19 | 62.74 | 50
4 | MALDAH | Kaliachak-I | Malda Mechanical | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Quotation Payment for Gayeshbari under SUJAPUR CCC in the District Of Malda |  |  | BILL/03551/2023-2024 | BP-2023-24-564 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 7.72 | 0 | 0 | 0
5 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2ND Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000280/2023-2024 | 3082/MAAD | 14/12/2023 | 01/11/2025 | MAHBUB AND SONS | 225.34 | 45.91 | 20.38 | 75
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000362/2023-2024 | 52/MAAD | 18/01/2024 | 01/04/2025 | WIST WATER SOLUTIONS PRIVATE LIMITED | 166.2 | 0 | 0 | 1
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Gayeshbari Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000138/2023-2024 | 1479/MAAD | 01/08/2023 | 01/07/2024 | PRITAM ENTERPRISE | 5.02 | 0 | 0 | 100
8 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Laying of Distribution System at Nayabasti, Jamirghata Station Road for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000273/2023-2024 | 3073/MAAD | 14/12/2023 | 12/02/2024 | GHOSH CONSTRUCTION | 18 | 12.77 | 70.95 | 100
9 | MALDAH | Kaliachak-I | Malda Mechanical | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | QUOTATION PAYMENT FOR GAYESHBARI W/S SCHEME PH NO 2 UNDER SUJAPUR CCC UNDER MALDA DISTRICT |  |  | BILL/00213/2025-2026 |  | 24/04/2025 | 24/04/2025 | W.B.S.E.D.C.LTD | 10.03 | 0 | 0 | 0
10 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | SM/15947 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000239/2024-2025 | 1693/MAAD | 19/11/2024 | 01/01/2026 | M/S MOON LIGHT CONSTRUCTION & CO. | 75.67 | 0 | 0 | 0
Total | [13 empty] | 683.07 | 67.87 | 9.94