## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nabinagar PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001012/2023-2024 | 3004427272 | 18/09/2023 | 17/12/2023 | W.B.S.E.D.C.LTD | 4.26 | 4.26 | 100 | 100
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 627/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 26.27 | 0 | 0 | 0
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Laying of Distribution System at Paschim Chamatola, Bankpara, Layagram, Puratun Tola for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000003/2023-2024 | 640/MAAD | 06/04/2023 | 05/06/2023 | SOVON KUMAR DAS | 50.45 | 39.03 | 77.36 | 95
4 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Laying of Distribution System at Lashratalla, Madhyapara & Nabinagar for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000002/2023-2024 | 639/MAAD | 06/04/2023 | 30/06/2024 | DHRITIPALI | 34.15 | 25.3 | 74.07 | 85
5 | MALDAH | Kaliachak-I | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Nabinagar Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017551) | Assistant Engineer - II | Junior Engineer-03 | ORD/000659/2023-2024 | 2687/MLMD | 11/08/2023 | 27/12/2025 | DEY ENTERPRISE.. | 65.66 | 41.89 | 63.8 | 45
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000241/2024-2025 | 1695/MAAD | 19/11/2024 | 19/12/2024 | DHRITIPALI | 31.71 | 0 | 0 | 0
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Nabinagar Piped Water supply scheme (Head Work Site & 2nd Tube well Site ) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000105/2023-2024 | 1412/MAAD | 20/07/2023 | 03/09/2023 | M/S DYNAMIC CONSTRUCTION | 14.64 | 10.1 | 68.99 | 100
8 | MALDAH | Kaliachak-I | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | QUOTATION PAYMENT FOR NABINAGAR W/S SCHEME T/W NO 1 UNDER KALIACHAK CCC UNDER MALDA DISTRICT |  |  | BILL/01613/2024-2025 | BP-2024-25-397 | 29/07/2024 | 29/07/2024 | W.B.S.E.D.C.LTD | 3.91 | 0 | 0 | 0
9 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Nabinagar Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000127/2023-2024 | 1470/MAAD | 01/08/2023 | 01/10/2024 | M/S A.B. CONSTRUCTION | 5.02 | 0 | 0 | 100
10 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000264/2023-2024 | 3018/MAAD | 06/12/2023 | 01/07/2025 | M/S AMIT KUMAR GUPTA | 164.67 | 51.82 | 31.47 | 75
11 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | SM/15949 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000277/2023-2024 | 3079/MAAD | 14/12/2023 | 13/12/2024 | SOFIQUL ISLAM | 151.63 | 0 | 0 | 15
Total | [13 empty] | 552.37 | 172.39 | 31.21