## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sakullapur Piped Water supply scheme (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000465/2022-2023 | 554/MAAD | 24/03/2023 | 08/05/2023 | MD. TALEB ALI | 7.32 | 5.64 | 77.1 | 100
2 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 629/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 4.29 | 0 | 0 | 0
3 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Laying of Distribution System for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000469/2022-2023 | 611/MAAD | 31/03/2023 | 30/05/2023 | M/S MOON LIGHT CONSTRUCTION & CO. | 57.45 | 54.87 | 95.51 | 95
4 | MALDAH | Kaliachak-II | Malda Mechanical | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Sukurullapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018013) | Assistant Engineer - II | Junior Engineer-03 | ORD/000664/2023-2024 | 2690/MLMD | 11/08/2023 | 08/06/2026 | ANIMA ENTERPRISE | 48.84 | 28.36 | 58.07 | 40
5 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000240/2024-2025 | 1694/MAAD | 19/11/2024 | 03/01/2025 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 31.56 | 0 | 0 | 0
6 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000229/2023-2024 | 1816/MAAD | 05/10/2023 | 01/06/2025 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 133.47 | 16.58 | 12.42 | 80
7 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000376/2023-2024 | 111/MAAD | 01/02/2024 | 01/08/2025 | MAHBUB AND SONS | 100.84 | 37.62 | 37.31 | 80
8 | MALDAH | Kaliachak-II | Malda Mechanical | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | SM/15950 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000124/2024-2025 | 1679/MLMD | 26/06/2024 | 27/08/2024 | SUBRATA SAHA | 0.78 | 0.77 | 99.08 | 0
Total | [13 empty] | 384.54 | 143.85 | 37.41